## Sheet1
Task | Hours | Done/Not | Notes | HIGH LEVEL PLAN
Learning swift | 16:30 | forever in progress | calculator app works | Week 1 | Learning Swift / Make basic app framework
Create tab view | 1:00 | done |  | Week 2 | Connect student scene to code
Give tabs icons and names | 0:30 | done | Had to download icons in very small png format, will look into creating own? | Week 3 | Individual student viewing scene
Giving each screen a view container | 1:00 | done |  | Week 4 | connect student edit and student scene
Learning about Views | 1:00 | done |  | Week 5 | Connect attendence and reward tracking
Learning about delegates | 0:30 | done |  | Week 6 | connect attendence scene to code
Learning about imageView/gesture recognizers | 1:00 | done |  | Week 7 | student progress coded/scene working
Creating my own UI objects | 1:00 | done |  | Week 8 | connect all elements with individual student summary
Designing Data model | 1:00 | done |  | Week 9 | finish requirements before making live
Designing Student View | 0:30 | done |  | Week 10 | Get app out for testing
Learning testing in xcode | 0:30 | done |  | Week 11 | Feedback on testing, make changes
learning about tableViews | 1:00 | done |  | Week 12 | Final changes and touch-ups
Creating Student View in storyboard | 1:00 | done
Create custom tableView cell for students | 1:00 | done
navigating navigation controllers | 1:00 | done
Create student tableView | 0:30 | done
create Student Add/Edit View | 1:00 | done
add components to Student View screen | 1:00 | done
make segue between navigation bar add item to Student Add/Edit View | 1:00 | done
make save/cancel segue on Add/Edit view | 1:00 | done
create tap gesture recognition for image | 0:30 | done
Connect tap gesture to code in Student Add/Edit | 0:30 | done
Student tableView cell to segue to Student Profile view | 0:30 | done
Add components to student Add/Edit screen | 0:30 | done
connect Edit nav item in Student Prof to segue to Student add/edit | 2:00 | done
planning other views | 0:30 | done
connect student table view to code | 1:00 | done
Code segue from cell to student View | 1:00 | done
implementing swipe to Delete Student | 1:00 | done
research NSCoding | 2:00 | done
Persisting Data! | 3:00 | done
debugging persisting data until it works | 2:00 | done
Fixing cell views | 0:30 | done
passing student data between segues | 1:00 | done
Create custom attendance object | 2:00 | done
make Date tableView in storyboard | 1:00 | done
implement date picker for adding dates to date tableView | 2:00 | done
enable/disable save button while editing in Student add/edit | 1:00 | done
fix cancel button in add/edit to dismiss situationally to view that called | 1:00 | done
code image adding from library or camera in Student Add/Edit | 1:00 | done
create tableView of Students for attendance dates | 1:00 | done | each date must reflect a new attendence… how to implement?
connect Attendance tableView to Date tableView | 1:00 | done
make each date reload a new attendanceView | 1:00 | done ish | having each date load it's own student list. More data…
make attedance view cell not grey when tapped | 0:30 | done
create attendance button objects | 1:00 | done
implement tap attendance selection | 1:00 | done
create custom progress object | 1:00 | done
create tableView for student Progress | 1:00 | done
add componenets to tableView in storyboard | 1:00 | done
make individual progress save for each student | 2:00 | made change from tableView for progress to having progress in Student profile screen in order to have it save.
load progress icons | 0:30 | done
Move progress from progress tableView to student profile | 1:00 | done
add progress variable to student object | 1:00 | done
try to make keyboard not hide text | 1:00 | done
try switching from stack view to scroll view for keyboard issue | 1:00 | done | changed back
chane back to stack view | 1:00 | done
create NSNotifications for keyboard hiding issue | 1:00 | done | fixed keyboard hiding text boxes
wrap progress object | 1:00 | Didn't have to wrap, just compressed button size
Connect progress object to code to track each individual student progress | 1:00 | done
make progress object highlight tapped button | 1:00 | done
Implement saving and editing of students own progress variable | 1:00 | done
push app to other phones for testing | 1:00 | done
attempt to make attendance save other than tapping outside of object | 2:00 | not done. Will fix with CoreData
alphabetize students when adding |  |  | FOR LATER
swtich to CoreData |  |  | FOR LATER
implement image scaling and cropping when picking image |  |  | FOR LATER